PARLIAMENT OF KENYA

12TH PARLIAMENT

THIRD SESSION

REPORT OF THE PLANNING COMMITTEE FOR SITTINGS OF THE SENATE IN KITUI COUNTY

16TH TO 20TH SEPTEMBER, 2019

Clerk’s Chambers

The Senate

Parliament Buildings

NAIROBI      	October, 2019

TABLE OF CONTENTS

INTRODUCTION	3

SUB-COMMITTEES OF THE PLANNING COMMITTEE	4

Senate Business and Committee Sittings Sub-Committee	5

Accommodation and Transport Sub-Committee	5

Media, Broadcasting, Audio and ICT Sub-Committee	6

Food and Beverage Sub-Committee	7

Security and Office Accommodation Sub Committee	7

BRIEFS FROM THE SUB-COMMITTEES	8

a)	Senate Business and Committee Sittings	8

Plenary Sessions	8

Committee Sittings	13

b)	MEDIA, BROADCASTING, AUDIO AND ICT	16

Parliamentary Broadcasting Unit	18

Audio	20

ICT Team	21

TRANSPORT	22

Office accommodation	24

Projects Team	25

c)	CATERING DEPARTMENT	26

Successes from the Senate Sittings In Kitui County	28

Challenges from the Senate Sittings In Kitui	29

Final Recommendations	31

Annexures	32

# INTRODUCTION

- Article 126 (1) of the Constitution of Kenya provides that a sitting of either House of Parliament may be held at any place within Kenya and may commence at any time that the House appoints.

- It is in line with this provision of the Constitution that on on 28th May, 2019, the Senate Business Committee resolved that a sitting of the Senate be held in Kitui County and on 13th June, 2019, the House unanimously adopted to hold its plenary and committee sittings in Kitui County from 16th to 20th September, 2019.

- To prepare and actualize the resolution of the Senate, the Clerk of the Senate vide a Memo dated 3rd June, 2019 constituted a Planning Committee comprising-

|  | Name | Designation |
| --- | --- | --- |
|  | Mr. Zakayo Mogere | Deputy Director, Legislative and Procedural Services/Chairperson, Planning Committee |
|  | Mr. George Wanyoko | Deputy Hansard Editor |
|  | Mr. Boniface Lenairoshi | Principal Clerk Assistant I |
|  | Ms. Elizabeth Muhia | Principal Legal Counsel 1 |
|  | Mr. Peter Adika | Principal Research Officer |
|  | Ms. Farhiya Ibrahim Ali | Principal Serjeant-At-Arms |
|  | Mr. George Otieno | Senior Clerk Assistant |
|  | Mr. Charles Munyua | Clerk Assistant I |
|  | Mr. Robert Masongo | Deputy Catering Manager |
|  | Mr. Martin Mukabi | Procurement Officer II |
|  | Mr. Innocent Mbaya | Clerk Assistant I (Secretariat) |
|  | Mr. Eric Kipng’eno | Personal Secretary I (Secretariat) |

- The Committee was tasked with the responsibility of organizing, planning and facilitating the necessary logistics to enable the Senate to sit in Kitui County. The Committee held a total of ….. sittings including two reconnaissance visits to the Kitui County; one by the Planning Committee and Technical officers and Senate Board of Management on 25th – 27th June, 2019 and 26th – 27th July, 2019 respectively.

- The Planning Committee further organized a courtesy visit by Senate leadership to the Leadership of the County Assembly and Governor of Kitui County on 21st August, 2019. The following Senators made the visit;

- Sen. Kenneth Lusaka, EGH, MP		Speaker of the

Senate

- Sen. James Orengo, EGH, MP			Minority Leader

- Sen. Mutula Kilonzo Junior, MP		Minority Whip

- Sen. Irungu Kang’ata, MP			Deputy Majority

Whip

- Mr. Mohamed Ali.					Deputy Clerk

- The Leadership met with their counterparts at the Kitui County Assembly. The Senate leadership thanked the County Assembly of Kitui for agreeing to host the Sitting of the Senate in the Counties and shared the programme for the sitting with the Speaker, Clerk and leadership of the County Assembly. A few amendments were proposed which were incorporated in the final programme. The Leadership also did a site inspection of the Chamber and committee meeting rooms to assess the readiness of the County Assembly to host the Sitting. The Senators were impressed by the progress and were optimistic that all arrangements would be ready ahead of the Sitting.

- The Senators later met with the Governor of Kitui County H.E. Charity Ngilu at her office; they thanked her for his cooperation towards the planning for the Sitting. The Senate delegation shared the draft programme for the event with the Governor and his County Executive. The governor later hosted lunch in honor of the delegation.

# SUB-COMMITTEES OF THE PLANNING COMMITTEE

- In discharge of its mandate, the Planning Committee established the following delivery units aimed at coordinating finer details of the Senate sittings in Kitui. The Sub-Committees were constituted as follows-

## Senate Business and Committee Sittings Sub-Committee

Members

- Mr. Boniface Lenairoshi		-	Team Leader

- Mr. George Otieno

- Mr. Peter Adika

- Mr. Charles Munyua

Roles

- Development of a programme of activities for the Senate in Kitui;

- Development of Order Paper for the Senate plenary;

- Development of the Agenda for Committees;

- Facilitate public invitations to the Senate;

- Facilitate appointments for meetings and briefings;

- Facilitate invitations to the Senate plenary and Committee meetings;

- Liaison with the County Assembly officers on requirements for the Senate and Committees and channeling them appropriately; and

- Any other role that is assigned from time to time.

## Accommodation and Transport Sub-Committee

Members

- Mr. Geroge Wanyoko		-	Team Leader

- Mr. Martin Mukabi

- Mr. Innocent Mbaya

- Mr. Samuel Kanuku

- Mr. Stephen Maru

Roles

- Facilitate and secure accommodation for 68 rooms for Senators;

- Facilitate and secure accommodation of the Senate Board of Management for 11 persons;

- Facilitate and secure five (5) 11seater vans;

- Facilitate and secure three (3) 4 x 4 SUVs;

- Source for ambulance services with medical personnel;

- Coordination of ground transport facilities and movement including availing of an up to date schedule of departures and arrivals on time.

- Prepare and coordinate the schedule of travel for Senators and staff and

- Any other role that is assigned from time to time.

## Media, Broadcasting, Audio and ICT Sub-Committee

Members

- Mr. Alex Rithi	-	Team Leader

- Ms. Josephine Karani

- Mr. Washington Otiato

- Mr. Enoch Bosire

- Ms. Maryanne Karanja

- Ms. Farida Ngasura

- Mr. Richard Njoroge

- Mr. Kenneth Opondi

Roles

- Ensuring sufficient internet connectivity in the County Assembly;

- Availing of Modems for YouTube live stream;

- Ensure installation of wireless access points;

- Avail of smart digital TVs in the Public Gallery, Media Centre, Parliamentary Broadcast Unit, Secretariat Room and the Lounge;

- Ensuring the installation of the Hansard software;

- Liaise with the County Assembly on the provision of a standby generator and fuel for the same;

- Liaise with the County Assembly to ensure that the chamber lights are working;

- Availing of public address system for committee rooms;

- Liaise with the Hansard Department and Stores for the provision foot pedals, head phones, extension sockets and flash disks in the Hansard box and Secretariat room;

- Ensuring that the equipment for outside broadcasting by Kenya Broadcasting Corporation (KBC) are delivered availed at the site on time;

- Ensure the airing of plenary live proceedings run smoothly;

- Ensure the committees sittings are covered as appropriate;

- Development of a media engagement and publicity plan for the event;

- Liaison between the Senate and the media houses and

- Any other role that is assigned from time to time.

## Food and Beverage Sub-Committee

Members

- Mr. Robert Masongo		-	Team Leader

- Ms. Rose Mailu

- Mr. Martin Madanji

- Ms. Musyoka Venza

Roles

- Supervise provision of all meals including teas, snacks and lunch for 350 persons;

- Ensure adequate dining room for all participants;

- Ensure appropriate furniture and cutlery for all participants;

- Supervise the outside caterer to ensure safety and hygienic environment for food handling;

- Ensure the availing of two (2) mobile toilets;

- Any other role that is assigned from time to time.

## Security and Office Accommodation Sub Committee

Members

- Mr. Douglas Mbuvi-	Team Leader

- Mr. Dominic Malonza

- Mr. Stephen Gikonyo

Roles

- Facilitate and ensure appropriate furniture for all Committee rooms, offices, Secretariat room, Media Centre and Lounge;

- Issuance of identification badges and accreditation cards for journalists;

- Issuance of car stickers for access of designated vehicles;

- Oversee the modification of areas to serve as committee rooms, Media centre, media centre, press centre, secretariat office and the lounge

- Supervision of paint works of the County Assembly, Chamber and corridors;

- Oversee the laying of carpet for the dome, Members lounge and committee rooms;

- Availing of two (2) walk-through scanners and baggage scanner;

- Ensure proper signage of offices, restrooms and general areas;

- Vetting of staff who will be engaged by the outside caterer for quality control;

- Liaison with the Kenya Police, relevant security agencies and the Kenya Airports Authority for appropriate services to the Senate;

- Any other role that is assigned from time to time.

# BRIEFS FROM THE SUB-COMMITTEES

- Upon conclusion of the sitting, the sub-committees came up with the following;

- Senate Business and Committee Sittings

### Plenary Sessions

- The Senate held a total of 3 plenary sittings, on Tuesday 17th, Wednesday 18th and Thursday, 19th September 2019.  The highlights of the plenary sittings are as follows: -

- The following Bills were read a First Time:

- The Constitution of Kenya (Amendment) Bill (Senate Bills No. 16 Of 2019) - (Sen. CPA. Farhiya Ali, MP and Sen. Mutula Kilonzo Junior, MP)

- The County Licensing (Uniform Procedures) Bill (Senate Bills No. 17 Of 2019) - (Sen. Mercy Chebeni, MP)

- The Elections (Amendment) Bill (Senate Bills No. 18 of 2019) - (Sen. Ephraim Maina, MP)

- The Alternative Dispute Resolution Bill (Senate Bills No. 19 Of 2019) - (Sen. (Arch.) Sylvia Kasanga, MP)

- The following Bill was debated at Second Reading stage:

- The County Tourism Bill (Senate Bills No. 5 of 2019) - (Sen. (Dr.) Agnes Zani, MP)

- The County Allocation of Revenue Bill (Senate Bills No. 8 of   2019) - (Chairperson, Standing Committee on Finance and Budget)

- The County Hall of Fame Bill (Senate Bills No. 39 of 2018) - (The Senate Majority Leader)

- The Street Vendors (Protection of Livelihood) Bill (Senate Bills No. 10 Of 2019) - (Chairperson, Standing Committee on Tourism, Trade and Industrialization)

- The following Motion was moved and considered:

Motion by the Senate Majority Leader and the Senate Minority Leader on eestablishment of Ad Hoc Committee to investigate Managed Equipment Services (MES) – Motion moved, debated and adopted.

- The following Petition was reported on and committed to respective Committees for consideration:

Report of the Standing Committee on Agriculture, Livestock and Fisheries on the Petition concerning challenges facing small scale tea growers in the Kenya Tea Development Agency (KTDA) – reported by the (Sen. Naomi Waqo on behalf of the Chairperson, Standing Committee on Agriculture, Livestock and Fisheries);

- The following Statements were sought and/or issued: -

- Statement on the successive failure of County Governments to meet the own source revenue (OSR) targets (Sen. George Khaniri, MP);

- Statement on the plight of Internally Displaced Persons (IDPs) – sought by the Senator for Makueni County (Sen. Mutula Kilonzo Junior, MP) from the Standing Committee on National Cohesion, Equal Opportunity and Regional Integration;

- Statement on the status of inclusion of persons with disabilities (PWDS) in the labour market – sought by Nominated Senator (Sen. (Dr.) Agnes Zani, MP) from the Standing Committee Labour and Social Welfare;

- Statement on the issues and status of operationalization of IFMIS in the 47 counties - sought by Nominated Senator (Sen. (Dr.) Agnes Zani, MP) from the Standing Committee on Finance and Budget;

- Statement on the rapid collapse of Kenya’s healthcare system – sought by Senator for Vihiga County (Sen. George Khaniri, MP) from the Standing Committee on Health;

- Statement on the status of asset registers in counties – sought by Senator for Vihiga County (Sen. George Khaniri, MP) from the Standing Committee on Devolution and Intergovernmental Relations;

- Statement on the unrest at Kisumu County Assembly – sought by Senator for Kisumu County (Sen. Fred Outa, MP) from the Standing Committee on National Security, Defence and Foreign Relations;

- Statement on the rising cases of insecurity in Tana River County – sought by Senator for Tana River County (Sen. Golich Juma Wario, MP) from the Standing Committee on National Security, Defence and Foreign Relations;

- Statement on the ‘International Day of Democracy’ (Sen. Abshiro Halake, MP);

- Statement on the Special Needs Education (Sen. (Dr.) Getrude Musuruve, MP)

- Statement on the provision of Immigration Services to Kenyans in the Northern Kenya region sought by Senator for Wajir County (Sen. (Dr.) Abdullahi Ali, MP) from the Standing Committee on National Security, Defence and Foreign Relations;

- Statement on the status of prisons in Kitui sought by Senator for Makueni (Sen. Mutula Kilonzo Junior, MP) from the Standing Committee on National Security, Defence and Foreign Relations;

- Statement on the terrorist attack at the African Inland Church (AIC) Garissa on 1st July, 2012, where 13 persons died and over 60 persons were injured, most of whom were from Kitui County sought by Senator for Kitui County (Sen. Enoch Kiio Wambua, MP) from the Standing Committee on National Security, Defence and Foreign Relations;

- Statement on the budget process at the county level of government (Chairperson of the Standing Committee on Finance and Budget);

- Statement on the activities of the Committee during the Sitting of the Senate in Kitui (Chairperson of the Sessional Committee on County Public Accounts and Investment);

- Statement by the Deputy Senate Majority Leader on the business of the Senate for the week beginning Tuesday, 24th September, 2019.

- The following Papers were laid on the Table of the Senate: -

  - Report of the Standing Committee on Finance and Budget on the County Allocation of Revenue Bill (Senate Bills No. 8 of 2019); and

  - Statement on the business of the Senate for the week commencing Tuesday, 24th September, 2019.

- The following invited dignitaries attended plenary Sittings of the Senate and sat at the Speaker's Gallery:

| Governors of Neighbouring Counties |  |  |
| --- | --- | --- |
|  | Gov. (Dr.) Alfred Mutua, EGH | Machakos County |
|  | Gov. (Prof.) Kivutha Kibwana, EGH | Makueni County |
|  | Gov. Martin Wambora, EGH | Embu County |
|  | Gov. Ali Korane, CBS | Garissa County |
|  | Gov. Major (Rtd) Dhadho Godhana | Tana River County |
|  | Gov. Muthomi Njuki, EGH | Tharaka Nithi County |
| Members of Parliament from Kitui County |  |  |
|  | Hon. (Dr.) Makali Mulu, MP | MP, Kitui Central |
|  | Hon. Edith Vethi Nyenze, MP | MP, Kitui West |
|  | Hon. Nimrod Mbai, MP | MP, Kitui East |
|  | Hon. Racheal Nyamai, MP | MP, Kitui South |
|  | Hon. David Mwalika Mboni, MP | MP, Kitui Rural |
|  | Hon. Gideon M. Mulyungi, MP | MP, Mwingi Central |
|  | Hon. Charles Ngusya Nguna, MP | MP, Mwingi West |
|  | Hon. Paul Musyimi Nzengu, MP | MP, Mwingi North |
|  | Hon. (Dr.) Irene Kasalu, MP | Women Representative, Kitui County |
| Speakers of County Assemblies |  |  |
|  | Hon. Florence Mwangangi, MCA | Speaker, Machakos County Assembly |
|  | Hon. Michael Nkaduda, MCA | Speaker, Tana River County Assembly |
|  | Hon. Douglas Mbilu, MCA | Speaker, Makueni County Assembly |
|  | Hon. Josiah M. Thiriku, MCA | Speaker, Embu County Assembly |
|  | Hon. David Mbaya, MCA | Speaker, Tharaka Nithi County Assembly |
|  | Hon. Ahmed Ibrahim Abass, MCA | Speaker, Garissa County Assembly |
| Clerks of County Assemblies |  |  |
|  | Mr. Elijah Mutambuki | Clerk, Kitui County Assembly |
|  | Mr. Abdullahi Hussein | Clerk, Tana River County Assembly |
|  | Mr. Robert Mwalu | Clerk, Makueni County Assembly |
|  | Mr. Jim Kauma | Clerk, Embu County Assembly |
|  | Mr. Amos Kiangwe | Clerk, Tharaka Nithi County Assembly |
|  | Mr. Mahmoud Santur | Clerk, Garissa County Assembly |
| Invited Dignitaries |  |  |
|  | Hon. David Musila, EGH | Former Senator for Kitui County, and currently Chairman of the National Museums of Kenya |
|  | Hon. Nyiva Mwendwa, EGH | Former MP, Kitui West Constituency |
|  | Mr. Nzamba Kitonga, SC | Former Chairman, Committee of Experts on constitutional review |
|  | Mr. Eric Mutua | Former Chairperson, Law Society of Kenya |
|  | Ms. Selessor Odipoh | Westminster Foundation for Democracy (WFD) |
|  | Ms. Roselyn Mungai | Ag. Country Director, AHADI |
|  | Mr. Japhet Masya | Former Clerk of the National Assembly |
|  | Prof. Geoffrey Muluvu | Vice Chancellor, South Eastern University of Kenya |

- The following groups visited and observed plenary Sittings of the Senate:

- Visiting Students and Teachers from Kitui Institute of Development Studies, Kitui County;

- Visiting Students and Teachers from Central Primary School in Kitui County;

- Visiting Students and Teachers from Muslim Primary School in Kitui County;

- Visiting residents of Migwani Ward, Mwingi West Constituency in Kitui County;

- Visiting Students and Teachers from St. Angela’s High School in Kitui County;

- Visiting Pupils and Teachers from Kitui School for the Deaf in Kitui County;

- Visiting Students and Teachers from St. Charles Lwanga Boys’ School in Kitui County;

- Visiting Students and Lecturers from Mulango Bible College in Kitui County;

- Visiting Pupils and Teachers from Central Primary School in Kitui County; and

- Visiting Students and Teachers from Kyondoni Mixed School in Kitui County.

### Committee Sittings

- The Senate Committees held sittings with various stakeholders and visited various institutions as follows: -

| S/No. | Committee Meeting | Date |
| --- | --- | --- |
|  | # Meeting between the Senate Leadership and the County Assembly Leadership. | 16.09.19 |
|  | # Meeting between Senators and County Assembly Members. | 16.09.19 |
|  | Senate Leadership Meeting with the Kitui County Leadership. | 16.09.19 |
|  | Meeting of the County Public Accounts and Investments Committee with Nyeri County Executive. | 17.09.19 |
|  | Standing Committee on Information, Communication and Technology meeting on 2G network with CAK connectivity in Tharaka, Nguuku and Ngomeni wards as a follow up from the Committee’s visit in August, 2018. | 17.09.19 |
|  | # Standing Committee on Finance and Budget meeting- - with counterpart County Assembly Committee. Stakeholders on the County Allocation of Revenue Bill, 2019. - Stakeholders on the County Allocation of Revenue Bill, 2019. | 17.09.19 |
|  | ### Standing Committee on Education visit to St. Michael's School for the Deaf and TVET centres. | 17.09.19 |
|  | ### Speaker’s Panel meeting | 17.09.19 |
|  | ### Senate Business Committee Meeting | 17.09.19 |
|  | ### Meeting of the County Public Accounts and Investments Committee with Machakos County Executive | 18.09.19 |
|  | ### Standing Committee on Justice Legal Affairs and Human Rights and the Committee on National Security, Defence and Foreign Relations visit to Kitui Prisons and Remand. | ### 18.09.19 |
|  | ### Standing Committee on Land, Environment and Natural Resources and the Committee on Roads and Transportation meeting with Cabinet Secretary Transport, KENHA and National Lands Commission on a Petition regarding compensation of land to the affected persons on the Kibwezi– Mutomo - Kitui road. | 18.09.19 |
|  | ### Standing Committee on Energy meeting on oil spillage in Thange River. | 18.09.19 |
|  | ### Standing Committee on Agriculture, Livestock and Fisheries public and stakeholders’ engagement on the Mung Bill (Ndengu) | 18.09.19 |
|  | ### Meeting of the County Public Accounts and Investments Committee with Makueni County Executive | 19.09.19 |
|  | ### Standing Committee on Health to meet County Executive on the budgetary allocation to the Health Sector against the County Budget, Financing of Maternal care, newborn and children healthcare including the levels of birth mortality and easy access to reproductive healthcare services and general morbidity in the County and interventions ensuing based on Sustainable Development Goals. | 19.09.19 |
|  | ### Sessional Committee on Delegated Legislation to meet with counterpart Committees from Kitui and Makueni County Assemblies to deliberate on the delegated legislation function and emerging issues. | 19.09.19 |
|  | ### Standing Committee on Roads and Transportation site inspection visit to county governments roads | ### 19.09.19 |

- MEDIA, BROADCASTING, AUDIO AND ICT

### Media

- The Planning Committee mandated the Media Relations Department to formulate a Media Strategy that would raise awareness in the public before and during the sittings in Kitui. The Media Relations Officers deployed to the Senate came up with a Media plan that included, interviews by the Leadership and other Senators.

- As part of the media plan the team drew up several advertisements which ran in both Radio and television stations targeted at the entire country. The team also made use of the Parliament’s Social media platforms in updating the activities of the event. The advertisements ran as follows:

Newspaper Advert

| MEDIA HOUSE | ACTIVITY |
| --- | --- |
| 1.Daily Nation | Published on Friday, 13th September |
| 2. The Standard | Published on Friday, 13th September |

Radio Advert

| S/No. | MEDIA HOUSE | ACTIVITY |
| --- | --- | --- |
|  | Athiani FM | Airing of Advert for one week (13th -16th Sept.) |
|  | County FM | Airing of Advert for one week (13th -16th Sept.) |
|  | Mbaitu FM | Airing of Advert for one week (13th -16th Sept.) |

Interviews

Below hereunder, are the TV and Radio interviews that were carried out by Senators before and during the sitting of the Senate in Kitui County Assembly on September 16th- 20th 2019:

| MEDIA HOUSE | PROGRAMME | SENATORS |
| --- | --- | --- |
| K24 | Interview | Speaker Ken Lusaka |
| County FM | Breakfast Show Live coverage from the Assembly precincts | Sen. Mutula Junior |
| Athiani FM | Breakfast | Sen. Wambua Kiio |
| Mbaitu FM | Breakfast | Sen. Kabaka Michael |
| Citizen/NTV/KTN/K24 | Live Coverage/Interview @Kitui County Assembly | Speaker Ken Lusaka Senators |

## Curtain Raiser

- The four daily newspapers and radio stations mentioned above carried stories informing the public of the Senate sittings outside parliament and on the reasons why the senate will hold its first sitting in Kitui County.

## Social Media

- The Parliamentary social media handles were updated regularly to capture the events taking place during the weeklong events.

The handles are on facebook page-Parliament of Kenya, Twitter                                   Senate- @senate-KE and @SENCommitteeKE.

The four media houses also updated their social media on the Senate event.

## Committee Coverage

- The Senate committees received favorable coverage in Kitui by both mainstream media (TV, print and radio stations) and in social media.

## Pictorials and Documentary

- Winex Media, was commissioned by the Senate to ensure overall pictorial and documentary coverage of all the events in Kitui County.

Recommendations

- The Senate Business Committee or a Kamukunji would be a good platform to implore Members on the intricacies of media etiquette including discussions on reasonable expectations and the need for the Senate to be more visible. Members need to be advised to cooperate with the media relation officers to appear for press interviews and planned shows in order to tell the senate story. The no show and unavailability by senators for media interviews does not augur well with media houses.

### PARLIAMENTARY BROADCASTING UNIT

Radio

- The team left Nairobi for Kitui on Monday 16th September 2019 and arrived safely around 12.30 hours. Installations works commenced in the afternoon and upon completion the systems were tested and found okay as well as the signal linking to the Broadcasting House (KBC studios).

The Radio Taifa transmitter 92.9 MHz that covers Kitui and its environs was not on air, and an alternative 101.70 MHz transmitter which relays Mwatu FM (a KBC regional FM station) which covers Kitui and its environs was sought. 93.10 MHz transmitter to relayed the signal during the Senate proceedings for the three days the Senate was in Kitui.

- One (1) radio technician for such an assignment posed a great challenge given the scope of work required in such coverage. Installation works were being done while the Senate committees were ongoing in the chambers.

Technical (TV)

- The team arrived at the venue on the 16th of September which was quite risky when it comes to rigging of equipment and testing in readiness for transmission, as it was on the eve of the plenary sittings. the team managed to do the rigging even though it inconvenienced the committee preparations and security arrangements that had already been put in place by the security team.

- Transmission of the plenary sittings and the CPAIC committee sittings was smooth on KBC, Senate TV, Heritage TV and YouTube. Transmission was undertaken with the graphics from the source. The team carried a character generator with a switcher which made the online YouTube off air quite good.

- All the invited guests and the public were able to follow the proceedings from the tents outside the chamber.

Satellite News Gathering

- The crew arrived on Monday 16th and immediately set up the equipment and ascertained that it was working well.

Throughout the plenary and the CPAIC committee sittings signals on both radio and TV were of the highest quality. The SNG equipment was permanently powered by the generator ensuring that there was no signal loss or glitch at any given time.

TV Production

- The team that had identified the camera positions during recce carried out the on the 25th-27th of June, 2019. setting up of the gallery and cameras was done on the same day the team arrived. The gallery was relatively close to the chamber entrance which made it easy for changes to be carried out whenever the need arose.

- Transmission of graphics was incorporated and integrated in the overall production of the Senate plenary and CPAIC Committees which made it easier for viewers on YouTube to follow the proceedings.

- The production team also managed to interview the Speaker of the Senate Hon. Lusaka on the KBC 1 pm news on Thursday 19th September,2019.

- The lighting was more sufficient making the pictures clearer and crisp. The cameras and the gallery equipment were powered by a generator.

## Proposals and Recommendation

- The Broadcast team should be brought on Board during such preparations early on time and preferably as part of the planning committee.

- Procurement related to broadcast should be done early to avoid last minute inconveniences.

- Setting up and rigging of equipment should be done 2 days earlier to forestall any unforeseen eventualities that can have a negative impact on the coverage.

- KBC and Parliament need to come up with a way through which a character generator and switcher can be acquired for use in outside broadcasts that involves the Senate whether plenary sittings or committees.

### Audio

- The Team observed that, the county had invested in two Conference Systems (Chamber Conference System & Committee Room 2 PA System), whereby committee room 2 having the hand held wireless P.A system. The Delegate Units of the Taiden Conference system in the chamber was up and running well. However, the wireless system in committee room 2 was not adequate to handle the committees’ activities sufficiently. Also the audio conference systems in the other committee rooms was also lacking.

- The Hansard Shared folder on the LAN was unstable and did not have a backup.

- There were regular power outages but the county had invested in a 20Kva UPS which could sustain the activities in the assembly chamber. Audio recording for Hansard purposes was uninterrupted during power outages since there was a separate backup UPS for the recording room and control room.

Recommendations

The Parliamentary Service Commission should consider to-

- Acquire Audio Distribution Press Box

- Have WAN/LAN Backup/ Redundant Paths

- Acquire Portable Computing devices

- Have a backup of the Hansard Server with Failover

- Encourage more staff benchmarking between Senate and county assemblies to help build capacity of the county assembly hansard/audio staff in audio recording, segmentation and note taking.

### ICT Team

- The ICT team represented by Mr. Enock Bosire, Ms. Maryanne Karanja, Ms. Ruth Nang’ole and Mr. Kenneth Opondi. The team was tasked to ensure the smooth running of all ICT systems during the sittings, and also to facilitate users in their day to day operations. The team’s duties included:

- Making sure that the Chamber System worked efficiently

- Ensuring sufficient internet connectivity in the County Assembly.

- Running You tube live proceedings during Committee and Chamber sessions

- Configuring and Installation of wireless access points.

- Installation of the Hansard System.

- Maintaining and uploading documents on the website in a timely manner.

- User Support services

- In the execution of their duty the team was able to:

- Ensure that internet bandwidth was increased from 6Mbps which was initially used in the County Assembly to 50Mbps.

- Perform network configurations, do structured cabling and making sure that all the 3 new Ruckus Access points were integrated in the Kitui network infrastructure and configured accordingly

- Offered timely user support services to our members of staff, e.g Installations of Case Viewer Software for the Hansard department.

- Live streamed of the Chamber and Committee sittings, in collaboration with the Broadcasting department.

- Configured other WiFi Access dongles on user PCs.

- Backed up all user information during this period by giving users external Hard Disks and Flash disks.

- However, some of the challenges experienced included; poor network connectivity from the County Assembly’s internet service provider due to slow response from ISP personnel, the chamber system inability to perform critical functions such voting, setting speaking time and limited conferencing capability and late delivery of procurement items from suppliers.

Recommendations

- The Procurement team needs to work together with ICT, to ensure that all required items are delivered on time.

- The respective County Assemblies need to put their Service Providers to task, and be able to get the best services and equipment needed.

- There should also be more preparatory visits to County Assemblies ahead of such sittings, to assess the infrastructure and verify whether the given suggestions and improvements have been implemented accordingly.

## TRANSPORT

- The Transport team was headed by Mr. George Wanyoko – Deputy Hansard Editor. The overall task of the transportation team was to ensure that all Senators and staff were well facilitated.

- There were fifteen (15) vans and seven (7) Prados which were used to ferry officers from their hotels to Kitui County Assembly every day.  A hired truck was used to transport equipment from Nairobi to Kitui Assembly. No damages of equipment or incident were reported.

- Transport team established adequate coordination mechanisms with the service provider and the planning committee to increase efficiency and to ensure issues were identified, discussed and resolved in a timely manner. There was also regular reporting between the transport and the planning committee on movement control activities and surface transport activities.

Recommendation

- Requisitioning lead time for logistics service should be improved to ensure efficient and timely delivery of service;

- There is need to dedicate adequate resources for policy development, oversight and quality assurance, on the status of vehicles to be hired/procured by Parliamentary Service Commission.

SERJEANT-AT-ARMS

Chamber Support

- The county assembly chamber was given little touch ups and reset to be used by the senate for the plenary business and committees (CPAIC). Chamber bar was improvised and control room reinforced for safety of mace. Three (3) orthopaedic was place in the chamber for comfort of senators with back problem. Senators and officers of the house smoothly carried out the house business with no hitch.

- A Speaker’s chair specifically made for the historic sitting was presented to the County Assembly speaker as a token of memento for remembrance.

- Schools and other visit were well coordinated both at speakers and public gallery.

Media gallery was well coordinated too.

Committee Support

- The team supported committee work as follows.

- Facilitated four (4) – Five (5) committee sitting at county assembly on daily bases

- Facilitated four (4) committee field visit

- Facilitated one (1) committee public hearing

House keeping

- The team was tasked with the responsibility of ensuring that all committee rooms, chamber, common user area, offices, gardens and tent area cleaned on daily basis. The county assembly assigned us eleven (11) causal workers to assist in cleanliness.

Escort and Transportation of items/equipment

- The Mace and other equipment/items were safely transported and brought back under police escort.

- The challenge experience was the catering tent was small to accommodate both the Senators and MCAs and the high number of police officers accessing the dining area.

General Security

- The team coordinated security in liaison with county security committee under the leadership of county commander. More than 200 police officers were deployed in County Assembly buildings, hotels security, Ithookwe showground- Ball game area, public hearing venues, field visit for committees, parking area and coverage for Avena half marathon.

- The major tasks performed by the officers included; Vehicle/foot security patrols, detecting of explosives with help of canines, traffic management, manning all entry/exit points, vehicle/human searches, sharing of security intelligence information, maintenance of law and order. No incident was reported.

Recommendations

- Personal security tips need to be taught and reminded to Senators and staffers when they operate outside their normal work stations.

- Service providers need to be identified on time so as to provide sufficient time for background checks vetting of their staff especially drivers of hired vehicles.

### Office accommodation

- The County Assembly of Kitui was instrumental in our effort to actualize our requirements for working space while at the sittings. After the visit by the planning committee and identification of a suitable contractor, the following offices were set up/identified within the county Assembly premises.

Leadership Offices

- The Senate Speaker, Deputy Speaker, Leaders of Majority and Minority were all accommodated in the main County Assembly building together with the Clerk of the Senate in offices generously given out by county assembly leadership and staff. The offices satisfactorily served the purpose.

Assembly Chamber

- The County Assembly chamber was given little touch ups and reset to be used by the senate for the plenary business and committees (CPAIC). Senators and officers of the house smoothly carried out the house business with no itch.

- It is also worth to note that a Speaker’s chair specifically made for the sitting was presented to the County Assembly speaker as a token of memento for remembrance.

Senators Lounge and Media and press centre

- The Planning committee recommended that the County Assembly car park be converted into lounge to cater for senators and members of staff.

### Projects Team

- The Planning Committee on its preparatory visits to the County Assembly to establish facts on the ground found that it was necessary to carry out a facelift of the chambers, corridors and some of the offices to be occupied by the Senate leadership by repainting and carrying out other minor alterations.

Scope of the Works

- The works generally involved creation of committee rooms, secretariat office, a lounge, public gallery and a media centre in the existing car sheds by fixing of canvas around the sheds with a matching linen at the ceiling and covering the loose ballast within the sheds with appropriate materials. Further works included refurbishment of the existing structures particularly the chamber, some offices and corridors by repainting of walls and ceilings. Other works comprised of improving the existing storm water drainage, clearing of site and spreading of ballast to set up a dome for catering services and installation of sockets and lighting at all makeshift committee rooms and offices.

Recommendations

- It is recommended that in future, a thorough evaluation of the condition of the buildings is conducted by Engineers to establish the actual status of the buildings and fixtures therein. It is also recommended that works should be awarded to contractors early enough for even better results. Despite the challenges highlighted above, the works were completed in time for the sittings.

- CATERING DEPARTMENT

- The Catering Department coordinated provision of meals including running teas for 400 Pax as well as cocktails hosted during the period of the Senate sittings Kitui. The Department delivered its mandate as follows-

- Daily check up on the status of Senators lounge and all Committee rooms;

- Provision of 10.00am & 4.00pm running teas to the Senators at the Members lounge and the Committees, Kitui Members of County Assembly, Senate staff, Kitui staff and the all invited County leaderships who were appearing at the committees;

- Provision of Lunch to the Senators, Members of County Assembly, Senate staff, Kitui staff and the all invited County leaderships who were appearing at the committees;

- Making sure tents were properly pitched to run the function and cleanliness was being carried out on daily basis;

- Seeing that Kitchen and Service staff were reporting on duty on time ready for production and service;

- Checking on and coming up with lunch and Snacks menus on the daily basis; and

- Seeing that food was of high hygiene, standards and quality befitting Senators.

Observations

The Parliamentary Catering staff, the contracted service provide, Hillary Food Hut and Caterers ensured that:

- 10.00am & 4.00pm teas to Senators lounge and Committees were served on time;

- Lunches at the tent were also served on time

- Instead of Serving 400 pax for the lunches the numbers of guests shot up on Tuesday, Wednesday and Thursday mostly due to the high number of security personnel providing security services and counties executives invited for committees’ sessions hence invited for lunch without prior booking and notice to the caterer as tabulated below:

|  | DATE | LUNCH | 10.00 A.M. | 4.00 P.M. | REMARKS |
| --- | --- | --- | --- | --- | --- |
| 1. | 16/9/2019 | 532 PAX | 486 PAX | 422 PAX |  |
| 2. | 17/9/2019 | 477 PAX | 412 PAX | 431 PAX |  |
| 3. | 18/9/2019 | 484 PAX | 427 PAX | 388 PAX |  |
| 4. | 19/9/2019 | 447 PAX | 438 PAX | 418 PAX |  |
| 5. | 20/9/2019 | 304 PAX | 473 PAX | 353 PAX |  |

- The Speakers Dinner for 120 persons at the Paradise Kitui Hotel, Kitui on Tuesday, 17th September,2019 was a success.

- the Cocktail in the Assembly grounds for the 250 Parliamentary and Kitui County staff facilitating the sitting of the Senate in Kitui County was also successful. The members of staff enjoyed the hospitality and bonded.

- Some of the challenges the team experienced were:

- Influx of guests to the dining areas as compared to the booked numbers;

- Erratic purchases from the service provider which hampered food supply on Thursday 19th Septemebr,2019;

- Delay by the Committee Clerks in informing the Service provider to book for late lunches for committees out for site visits;

- Long working hours by catering staffs in preparation of the next day’s work.

Recommendations

The following are the recommendation which will make future services a success;

- The security personnel, invited guests appearing before the committees and Members of the County Assemblies to be factored in the provision of running teas and lunches and cocktails respectively;

- Committee Clerks to be booking for late lunches in case they have sites visits.

# SUCCESSES FROM THE SENATE SITTINGS IN KITUI COUNTY

- The Sittings of the Senate in Kitui County was made pursuant to Article 126 of the Constitution and it was a success;

- The Senate and its Committees were able to interact directly with county leaders and citizens in their context. This helped foster understanding between the Senate, the various county governments and the citizens in Kitui and enhance the profile of the Senate in representing and protecting the interests of counties and their governments;

- The Sittings of the Senate and its Committees managed to attract substantial media coverage during the week and in the weeks preceding it. This helped enhance the visibility of the Senate and knowledge among Kenyans as to the work of the Senate;

- The Senate, both in plenary and its Committees, was able to address the most pressing concerns of the people in the region, including a meeting on 2G network with CAK connectivity in Tharaka, Nguuku and Ngomeni wards as a follow up from the Committee’s visit in August, 2018., Standing Committee on Finance and Budget meeting	with counterpart County Assembly Committee and stakeholders on the County Allocation of Revenue Bill, 2019 and on the County Allocation of Revenue Bill, 2019, Standing Committee on Education visit to St. Michael's School for the Deaf and TVET centres, Standing Committee on Land, Environment and Natural Resources and the Committee on Roads and Transportation meeting with Cabinet Secretary Transport, KENHA and National Lands Commission on a Petition regarding compensation of land to the affected persons on the Kibwezi– Mutomo - Kitui road, Standing Committee on Agriculture, Livestock and Fisheries public and stakeholders’ engagement on the Mung Bill (Ndengu), Standing Committee on Energy meeting on oil spillage in Thange River, Standing Committee on Health  meeting with  County Executive on the budgetary allocation to the Health Sector against the County Budget, Financing of Maternal care, newborn and children healthcare including the levels of birth mortality and easy access to reproductive healthcare services and general morbidity in the County and interventions ensuing based on Sustainable Development Goals, Sessional Committee on Delegated Legislation meeting  with counterpart Committees from Kitui and Makueni County Assemblies to deliberate on the delegated legislation function and emerging issues and Standing Committee on Roads and Transportation site inspection visit to county governments roads.

- Various dignitaries and leaders of the host and neighbouring Counties attended sittings of the Senate, in addition to interaction through sporting activities and dinner hosted by the Hon. Speaker of the Senate.,

- Senators were able to interact with members of the host County Assembly, both formally whereby transfer of skills and sharing of experiences took place, as well as informally through the various side events, including dinner and sports. These helped in networking and capacity building for the Members of the County Assembly.

- Senate staff were able to interact with the staff of the host County Assembly, both formally whereby transfer of skills and sharing of experiences took place, as well as informally through the various side events. These helped in networking and capacity building for the County Assembly.

- The sittings drew a big number of Senators, staff, media, invited guests and the general public to Kitui thereby creating an economic impact in the county and the region through hotels bookings, restaurants and transport.

# CHALLENGES FROM THE SENATE SITTINGS IN KITUI

- The wireless system in committee room 2 was not adequate to handle the committees’ activities sufficiently.

- Lack of the audio conference systems in some committee rooms;

- Poor network connectivity from the County Assembly’s internet service provider due to slow response from ISP personnel, the chamber system inability to perform critical functions such voting, setting speaking time and limited conferencing capability and late delivery of procurement items from suppliers.

- Delay in setting up and rigging of equipment by the KBC crew.

- Erratic power at the County Assembly caused the KBC crew and PBU to use a generator for their operations.

- The catering tent was small to accommodate both the Senators and MCAs and the high number of police officers accessing the dining area.

- Influx of guests to the dining areas as compared to the booked numbers;

- Erratic purchases from the service provider which hampered food supply on Thursday 19th Septemebr,2019;

- Delay by the Committee Clerks in informing the Service provider to book for late lunches for committees out for site visits;

- Long working hours by catering staffs in preparation of the next day’s work.

- There was late delivery of procurement items from suppliers. The access points were not delivered on time, therefore derailing the process of mounting and installations of ICT equipment.

- Some Senators did not check in on the days they were supposed to check into their hotels yet did not alert the planning team in advance.

- Cargo movement contractor did not provide loaders and off loaders of cargo at points of origin and destination.

- With respect to TV interviews, the major challenge experienced was failure to show up for media interviews and shows by Senators with some members cancelling as late as one hour to the slotted interview. No show by Members to various TV shows as well as lack of co-operation by members to attend TV and Radio interviews citing busy schedules or non-availability was a challenge and caused disappointments with the various media houses and as a result Media Officers had to mend relationships.

# FINAL RECOMMENDATIONS

- There is need to factor the Sittings of the Senate in the counties in the Senate work plans and budget.

- There is need for technical teams to make more visits to the counties during planning for Senate sittings outside Nairobi.

- It is proposed that area Members of National Assembly be invited to the Sitting to cultivate good relations.

- As resolved by the Senate, plans for the next sittings of the Senate outside Nairobi should start early.

# ANNEXURES

MOTION- SITTINGS OF THE SENATE OUTSIDE PARLIAMENT BUILDINGS, NAIROBI

(The Senate Majority Leader)

AWARE that the Senate of Kenya as established in the Constitution plays a critical role in the linkage of the devolved governments and the national government by representing and serving the interests of the counties and their governments;

FURTHER AWARE that on 21st June 2018, the Senate resolved to hold plenary and Committee sittings in Uasin Gishu County from 24th to 28th September, 2018, and further resolved that similar sittings be held in all regions of the country during the term of the current Parliament;

NOTING that the Senate held its first plenary and Committee sittings away from Nairobi in Uasin Gishu county from 24th – 28th September, 2018 providing an opportunity for several sectors of society to directly engage with the legislative arm of government through public participation on various issues, as well as participate in oversight through inspection of various projects and programs of national and county governments;

COGNIZANT that holding the plenary and Committee sittings of the Senate away from the traditional premises at the Parliament Buildings in Nairobi has great potential to, among others –

- enhance the interaction between the Senate and county governments;

- bring the Senate closer to the counties and the general public;

- provide an opportunity to members and staff of county assemblies to learn and borrow best practices from the Senate;

- promote the role and work of the Senate;

- highlight existing opportunities for people to get involved in the work of the Senate;

- develop and strengthen capacity and partnerships at the county level; and

- enhance public awareness regarding the Business of the Senate.

NOW THEREFORE, pursuant to Article 126 (1) of the Constitution and Standing Order 31 (1) of the Senate, the Senate resolves that its plenary and committee sittings be held in Kitui County from 16th to 20th September, 2019.

REPUBLIC OF KENYA

THE SENATE

12th PARLIAMENT-THIRD SESSION

THE SECOND SENATE COUNTY SITTINGS

AT

KITUI COUNTY

15th to 20th September, 2019

# PROGRAMME

| # DAY ONE SUNDAY 15TH SEPTEMBER, 2019 |  |  |  |
| --- | --- | --- | --- |
| # All day arrivals at Kitui County and check in at respective hotels. |  |  |  |
| # 5:00 – 6:00 p.m.; # Legislative and Procedural Briefing (Secretariat); # County Assembly Chamber. |
| # DAY TWO: MONDAY 16TH SEPTEMBER, 2019 |  |  |  |
| # Item | # Time | # Activity | # Venue |
|  | # 8:30 - 4:00 p.m. | # Staff Exchange between Directorates and Departments | # County Assembly Chamber |
|  | # 10:00 – 11:00 a.m. | # Meeting between the Senate Leadership and the County Assembly Leadership. | # Committee Room |
|  | # 11:00 – 12:00 Noon | # Meeting between Senators and County Assembly Members | # County Assembly Chamber |
|  | # 12:00 - 1:00 p.m. | # Senate Leadership Meeting with the Kitui County Leadership | # Office of the Governor, Kitui County. |
|  | # 1:00 – 2:30 p.m. | # Lunch | # Dome |
|  | # 4:00 - 6:00 p.m. | # Ball games - Senators vs Members of the County Assembly | # Ithookwe Showground |
| # DAY THREE: TUESDAY 17TH SEPTEMBER, 2019 |  |  |  |
| # Item | # Time | # Activity | # Venue |
|  | # 8:30 – 4: 00 p.m. | ### Staff Benchmarking Exchange Programme between Directorates and Departments. | # Directorates and Departments Offices |
|  | # 9:00 – 1:00 p.m. | ### Meeting of the County Public Accounts and Investments Committee with Nyeri County Executive. | # County Assembly Chamber |
|  | # 9:00 – 1:00 p.m. | # Standing Committee on Information, Communication and Technology meeting on 2G network with CAK connectivity in Tharaka, Nguuku and Ngomeni wards as a follow up from the Committee’s visit in August, 2018. | # Committee Room 2 |
|  | # 9:00 – 1:00 p.m. | # Standing Committee on Finance and Budget meeting- - with counterpart County Assembly Committee. - Stakeholders on the County Allocation of Revenue Bill, 2019 | # Boardroom |
|  | # 9.00 - 1.00 p.m. | ### Standing Committee on Education visit to St. Michael's School for the Deaf and TVET centres. | # Field visit |
|  | # 11:00 – 12:00 p.m. | # Speaker’s Panel meeting | # Committee Room |
|  | # 12:00 – 1:00 p.m. | # Senate Business Committee Meeting | # Committee Room |
|  | # 1:00 – 2:00 p.m. | # Lunch | # Dome |
|  | # 2:30 – 6:30 p.m. | # SENATE PLENARY | # COUNTY ASSEMBLY CHAMBER |
|  | # 7:30 – 9:00 p.m. | # Dinner Hosted by the Speaker of the Senate | # Parkside Villa Hotel |
| # DAY FOUR: WEDNESDAY, 18TH SEPTEMBER, 2019 |  |  |  |
| # Item | # Time | # Activity | # Venue |
|  | # 8:30 – 4: 00 p.m. | ### Staff Benchmarking Exchange Programme between Directorates and Departments. | # Directorates and Departments Offices |
|  | # 9:00 – 1:00 p.m. | ### Meeting of the County Public Accounts and Investments Committee with Machakos County Executive | # County Assembly Chamber |
|  | # 9:00 – 1:00 p.m. | Standing Committee on Justice Legal Affairs and Human Rights and the Committee on National Security, Defence and Foreign Relations visit to Kitui Prisons and Remand. | # Field visit |
|  | # 9:00 – 1:00 p.m. | Standing Committee on Land, Environment and Natural Resources and the Committee on Roads and Transportation meeting with Cabinet Secretary Transport, KENHA and National Lands Commission on a Petition regarding compensation of land to the affected persons on the Kibwezi– Mutomo - Kitui road. | # Field Visit |
|  | # 9:00 – 1.00 p.m. | ### Standing Committee on Energy meeting on oil spillage in Thange River. | # Committee Room |
|  | # 9:00 – 1.00 p.m. | ### Standing Committee on Agriculture, Livestock and Fisheries public and stakeholders’ engagement on the Mung Bill (Ndengu) | # Kitui Multi-Purpose Hall. |
|  | # 1:00 – 2:00 p.m. | # Lunch | # Dome |
|  | # 2:30 – 6:30 p.m. | # SENATE PLENARY | # COUNTY ASSEMBLY CHAMBER |
| # DAY FIVE: THURSDAY, 19TH SEPTEMBER, 2019 |  |  |  |
| # Item | # Time | # Activity | # Venue |
|  | # 8:30 – 4: 00 p.m. | ### Staff Benchmarking Exchange Programme between Directorates and Departments. | # Directorates and Departments Offices |
|  | # 9:00 – 1:00 p.m. | ### Meeting of the County Public Accounts and Investments Committee with Makueni County Executive | # County Assembly Chamber |
|  | # 9:00 – 1:00 p.m. | Standing Committee on Health to meet County Executive on the budgetary allocation to the Health Sector against the County Budget, Financing of Maternal care, newborn and children healthcare including the levels of birth mortality and easy access to reproductive healthcare services and general morbidity in the County and interventions ensuing based on Sustainable Development Goals. | # Committee Room 2 |
|  | # 9:00 – 1:00 p.m. | ### Sessional Committee on Delegated Legislation to meet with counterpart Committees from Kitui and Makueni County Assemblies to deliberate on the delegated legislation function and emerging issues. | # Boardroom |
|  | # 9:00 – 1.00 p.m. | Standing Committee on Roads and Transportation site inspection visit to county governments roads | # Field visit. |
|  | # 1:00 – 2:00 p.m. | # Lunch | # Dome |
|  | # 2:30 – 6:30 p.m. | # SENATE PLENARY | # COUNTY ASSEMBLY CHAMBER |
|  | # 6:30 p.m. | # Debriefing by the Clerk of the Senate | # Dome |
| # DAY SIX: FRIDAY, 20TH SEPTEMBER, 2019 |  |  |  |
| # Item | # Time | # Activity | # Venue |
| # 1. | # 6.30 a.m. | # Kitui – Avena Half Marathon (Hon. Speaker to flag off) | # Mutomo |
| # 3. | # 9:00 – 12: 00 Noon. | # Staff Benchmarking Exchange Programme between Directorates and Departments. | # Directorates and Departments Offices |
| # 4. | # 1:00 – 2:00 p.m. | # Lunch | # Dome |
| # 5. | # 3.00 pm | # Depart for Nairobi |  |

Appendixes:

- Order Paper for Tuesday, 17th September, 2019

- Weekly Programme of Senate Business for the week commencing 17th September, 2019

- Weekly Schedule of Committee Meetings (17th to 20th September, 2019)

Published by:

Clerk of the Senate/Secretary,

Parliamentary Service Commission

Parliament Buildings

NAIROBI

APPROXIMATE EXPENDITURE FOR SENATE SITTINGS IN KITUI COUNTY

| No. | Item Description | Supplier | Cost (Kshs.) |
| --- | --- | --- | --- |
| 1. | Photography, Videography Services and Documentary Production | M/s Okwood Ventures Limited | 1,480,000.00 |
| 2. | Drinking Water for use during the Sittings | M/s Hillary Food Hut Limited | 144,000.00 |
| 3. | Radio Advertisements | M/s Athiani FM (Athiani Holdings Limited) | 290,000.00 |
|  |  | M/s County FM | 232,000.00 |
|  |  | M/s Mbaitu FM (Eastern Broadcasting Corporation Ltd.) | 324,800.00 |
| 4. | Speaker’s welcoming dinner | M/s Kitui-Mwingi Parkside Motel Ltd. | 819,018.00 |
| 5. | Clerk’s Cocktail | M/s Kitui-Mwingi Parkside Motel Ltd. | 810,070.40 |
| 6. | Hire of furniture for Boardrooms, temporary offices and the Multipurpose Hall | M/s Let’s Go Party Tents | 730,224.00 |
| 7. | Ground transport services | M/s Digital Marine Ship Chandlers Ltd. | 4,306,060.00 |
| 8. | Hire of tents, various catering furniture and mobile executive toilets | M/s All Tymes Tents Ltd. | 4,906,927.00 |
| 9. | Provision of outside catering services | M/s Hillary Food Hut Limited | 5,800,000.00 |
| 10. | Procurement of various ICT equipment and services | M/s Senar Technologies Limited | 773,850.00 |
| 11. | Dedicated 50mbps internet bandwidth | M/s Safaricom PLC. | 308,154.00 |
| 12. | A replica of the Senate Speaker’s Chair | M/s Bukina Technology | 300,000.00 |
| 13. | Hire of public address system for use in committee rooms | M/s Pillar Audio Visual Services | 828,000.00 |
| 14. | Minor renovation and repair works at the county assembly of Kitui | M/s Breti Trading Agencies Ltd. | 798,000.00 |
| 15. | Live Coverage of plenary proceedings of the Senate in the county assembly of Kitui on television and radio | M/s Kenya Broadcasting Corporation | 2,400,000.00 |
| 16. | Accommodation facilities for Senators | M/s Kitui-Mwingi Parkside Motel Ltd. | 1,566,000.00 |
|  |  | M/s Kitui Villa | 369,850.00 |
|  |  | M/s Kenya Forest Research Institute | 258,000.00 |
|  |  | M/s Kitui Premier Resort | 520,000.00 |
|  |  | Total | 27,964,953.40 |

LIST OF SENATORS

| List of Senators - Senate Sitting in Kitui County |  |
| --- | --- |
| S/No. | Name |
|  | Sen. Kenneth Makelo Lusaka |
|  | (Sen. Prof.) Kithure Kindiki |
|  | Sen. Wario Golich Juma |
|  | Sen. (Eng.) Ephraim Mwangi Maina |
|  | Sen. Charles Reubenson Kibiru |
|  | Sen. Malachy Charles Ekal Imana |
|  | Sen. Samuel Losuron Poghisio |
|  | Sen. Kipchumba Murkomen |
|  | Sen. Gideon Kipsielei Towett Moi |
|  | Sen. Malalah Cleophas Wakhungu |
|  | Sen. Sitswila Amos Wako |
|  | Sen. James Orengo |
|  | Sen. Naomi Jilo Wago |
|  | Sen. Agnes Zani |
|  | Sen. Judith Ramaita Pareno |
|  | Sen. Beatrice Kwamboka Makori |
|  | Sen. Masitsa Naomi Shiyonga |
|  | Sen. Rose Ogendo Nyamunga |
|  | Sen. Isaack Mwaura |
|  | Sen. Getrude Musuruve Inimah |
|  | Sen. Mohamed Faki Mwinyihaji |
|  | Sen. Juma Boy Issa |
|  | Sen. Stewart Mwachiru Madzayo |
|  | Sen. Loitiptip Anuar |
|  | Sen. Jones Mwashushe Mwarume |
|  | Sen. Enoch Kiio Wambua |
|  | Sen. Boniface Mutinda Kabaka |
|  | Sen. Irungu Kang'ata |
|  | Sen. Wamatangi Paul Kimani |
|  | Sen. Steve Ltumbesi Lelegwe |
|  | Sen. (Prof.) Kamar Jepkoech Margaret |
|  | Sen. Samson K Cherarkey |
|  | Sen. John Kinyua Nderitu |
|  | Sen. Susan Wakarura Kihika |
|  | Sen. Ledama Ole Kina |
|  | Sen. Philip Salau Mpaayei |
|  | Sen. Aaron Kipkirui Cheruiyot |
|  | Sen. Christopher Andrew Langat |
|  | Sen. Khaniri George |
|  | Sen. Moses Otieno Kajwang |
|  | Sen. Samson Kagengo Ongeri |
|  | Sen. Milgo Alice Chepkorir |
|  | Sen. Millicent Omanga |
|  | Sen. Christine Zawadi Gona |
|  | Sen. Mary Yiane Seneta |
|  | Sen. Falhada Dekow Iman |
|  | Sen. Farhiya Ali Haji |
|  | Sen. Petronila Were Lokorio |
|  | Sen. Abshiro Soka Halake |
|  | Sen. Sylvia Mueni Kasanga |
|  | Sen. Prengei Victor |
|  | Sen. Mercy Chebeni |
|  | Sen. Dullo Fatuma Adan |
|  | Sen. Peter Njeru Ndwiga |
|  | Sen. Micheal Maling'a Mbito |
|  | Sen. Moses Wetangula |
|  | Sen. Johnson Arthur Sakaja |
|  | Sen. Mohammed Maalim Mahamud |
|  | Sen. Mohamed Yussuf Haji |
|  | Sen. Godana Hargura |
|  | Sen. Mithika Linturi Franklin |
|  | Sen. Jnr.Mutula Kilonzo |
|  | Sen. Paul Githiomi Mwangi |

LIST OF STAFF

| S/No. | Name | Designation |
| --- | --- | --- |
|  | Mr. J.M. Nyegenye | Clerk of the Senate |
|  | Ms. Eunice Gichangi | Deputy Clerk |
|  | Mr. Mohamed Ali | Deputy Clerk |
|  | Dr. Johnson Okello | Director, Legal Services |
|  | Mr. Njenga Ruge | Director Legislative & Procedural Services |
|  | Mr. Njenga Njuguna | Director |
|  | Mr. Joel Irungu | Ag. Director, Finance and Admin |
|  | Mrs. Gladys Ndeda | Hansard Editor |
|  | Maj. (Rtd.) Samson Sorobit | Chief Serjeant-At-arms |
|  | Mr. Dan Ajele | Chief Procurement Officer |
|  | Mr. J.M. Nyegenye | Clerk of the Senate |
|  | Mr. Zakayo Mogere | Deputy Director, Legislative Services |
|  | Mr. Boniface Lenairoshi | Principal Clerk Assistant 1 |
|  | Mr. Stephen Gikonyo | Senior Clerk Assistant |
|  | Ms. Josephine Karani | Head, PBU / Coordinator |
|  | Mr. Innocent Mbaya | Clerk Assistant I |
|  | Mr. Charles Munyua | Clerk Assistant I |
|  | Mr. Stephen Maru | Senior SAA II |
|  | Eng. Dominic Malonza | Construction Management Officer |
|  | Mr. Douglas Mbuvi | Security Officer I |
|  | Mr. Maxwell Chomba | Electrical Engineer |
|  | Ms. Maryanne Karanja | ICT Officer II |
|  | Mr. Robert Masongo | Deputy Catering Manager |
|  | Mr. Washington Otiato | Media Relations Officer |
|  | Mr. Kenneth Opondi | ICT Assistant |
|  | Mr. Ian Otieno | Audio Technician |
|  | Mr. Justus Mitau | Driver |
|  | Mr. Alex Ndung’u | Driver |
|  | Ms. Eunice Nyaga | Personal Assistant |
|  | Ms. Ann Mary Mutegi | Personal Secretary II |
|  | Mr. Sakari Muliro | Office Attendant |
|  | Mr. Victor Kilimo | Personal Assistant |
|  | Ms. Abigail Jemutai | Secretary |
|  | Mr. Ramadhan Chebiego | Office Assistant |
|  | Mr. Benard Maloma | Policy Analyst |
|  | Ms. Eunice A. Otieno | Secretary |
|  | Mr. Zuber Akhoya | Office Assistant |
|  | Ms. Florence Kaba | Personal Assistant |
|  | Ms. Christine Mwaura | Secretary |
|  | Ms. Felistus K. Mutune | Personal Secretary |
|  | Alicia Ndanu Mang’ati | Office Assistant |
|  | Ms. Kaltuma Haro Sime | Personal Secretary |
|  | Mr. Abel Kachu | Research Officer |
|  | Mr. Eliud Maina Wanja | Personal Assistant |
|  | Mr. David Muriuki Ndwiga | Personal Assistant |
|  | Mr. Eric Kiplimo | Personal Assistant |
|  | Mr. Charles Eric Musyoka | Personal Assistant |
|  | Ms. Irene Jambi Letiwa | Secretary |
|  | Mr. Victor Okeyo Oindo | Research Officer |
|  | Mr. Peter Mbai | Personal Assistant |
|  | Mr. George Wanyoko | Deputy Hansard Editor |
|  | Peter Adika | Principal Research Officer |
|  | Ms. Farhiya Ali | Principal SAA |
|  | Mr. George Otieno | Senior Clerk Assistant |
|  | Mr. Martin Mukabi | Procurement Officer |
|  | Mr. Eric Kipng’eno | Personal Secretary I |
|  | Ms. Carolyne Cheruiyot | Legal Counsel I |
|  | Ms. Sophie Salamba | Personal Secretary I |
|  | Ms. Fatuma Issa | Personal Secretary II |
|  | Ms. Jackline Oketch | Secretarial Assistant |
|  | Mr. Brown Mwangi | Office Attendant |
|  | Ms. Agnes Muchoki | Senior Secretary |
|  | Mr. Gabriel Nyongesa | Driver |
|  | Ms. Josephine Galsaraco | Office Attendant |
|  | Mr. Mwalimu Bakari | Office Attendant |
|  | Mr. Benard Otoro | Driver PSC |
|  | Mr. David Barasa | Security Aide |
|  | Mr. Julius Ariwomoi | Principal Clerk Assistant I |
|  | Mr. Ibrahim Leruk | Senior Clerk Assistant |
|  | Mr. Joseph Mwangi | First Clerk Assistant |
|  | Ms. Kavata Musyoka | First Clerk Assistant |
|  | Ms. Rose Mudibo | Second Clerk Assistant |
|  | Mr. Victor Bett | Second Clerk Assistant |
|  | Mr. Christopher Gitonga | Second Clerk Assistant |
|  | Mr. Peter Mulesi | Second Clerk Assistant |
|  | Mr. Charles Ngatia | Second Clerk Assistant |
|  | Ms. Mwanate Shaban | First Clerk Assistant |
|  | Ms. Carol Namunyak | Second Clerk Assistant |
|  | Mr. Crispus Njogu | Second Clerk Assistant |
|  | Ms. Gloria Wawira | Second Clerk Assistant |
|  | Mr. Yusuf Shimoy | Second Clerk Assistant |
|  | Ms. Diana Munene | Secretary |
|  | Ms. Pamela Odhiambo | Secretary |
|  | Mr. Hassan Odhowa | Principal Research Officer |
|  | Ms. Marale Sande | Research Officer |
|  | Mr. Said Osman | Research Officer |
|  | Dr. Christine Sagini | Research Officer |
|  | Ms. Claire Kidombo | Research Officer |
|  | Mr. Humphrey Ringera | Research Officer |
|  | Mr. Donald Manyala | Research Officer |
|  | Mr. Elly Atamba | Research Officer |
|  | Ms. Ann Kigoro | Research Officer |
|  | Ms. David Ng’eno | Research Officer |
|  | Mr. Mariko Roche | Office Assistant |
|  | Mr. Shinina Oloitiptip | Office Assistant |
|  | Mr. Charles Ondigi | Deputy Hansard Editor |
|  | Mr. Tom Ongalo | Senior Assistant Hansard Editor |
|  | Mr. Abdulmajid Ali | Senior Assistant Hansard Editor |
|  | Ms. Hortensiah Nyawira | Senior Assistant Hansard Editor |
|  | Mr. Brian C. Kiberass | Assistant Hansard Editor |
|  | Ms. Emma Muricho | Hansard Reporter I |
|  | Ms. Carolyn Njuki | Hansard Reporter II |
|  | Ms. Ruth Vusaka | Hansard Reporter II |
|  | Mr. Frederick Werimo | Hansard Reporter II |
|  | Mr. John Kariuki | Hansard Reporter III |
|  | Mr. Erick Kipkoech | Hansard Reporter II |
|  | Ms. Winnie Mandela | Hansard Reporter II |
|  | Ms. Concepta Owino | Hansard Reporter III |
|  | Mr. Richard Njoroge | Electronics Officer, II |
|  | Mr. Chwala Wekesa | Electronics Officer I |
|  | Ms. Carolyn A. Ng’onga | Personal Secretary |
|  | Mr. Victor Kamau | Office Assistant |
|  | Ms. Shirley Milimu | Intern |
|  | Mr. Kevin K. Korir | Intern |
|  | Ms. Beverlyne Elavuna | Intern |
|  | Mr. Kelvin Makumi | Intern |
|  | Ms. Brenda Nyaundi | Intern |
|  | Ms. Joyce Kakya | Intern |
|  | Mr. Lawrence Amolo | Principal Clerk Assistant I |
|  | Mr. Daniel chania | Principal Clerk Assistant II |
|  | Ms. Marya Adjibodou | Principal Clerk Assistant II |
|  | Mr. Enoch Bosire | Principal ICT Officer |
|  | Caroline Kinyua | Senior Clerk Assistant |
|  | Ms. Angela Macharia | Clerk Assistant II |
|  | Ms. Lilian Osundwa | Clerk Assistant II |
|  | Ms. Getrude Nthiiri | Clerk Assistant II |
|  | Ms. Mitchelle Osok | Clerk Assistant II |
|  | Ms. Ruth Nangóle | ICT Officer II |
|  | Mr. Shadrack Kaberia | Librarian Officer II |
|  | Mr. Lawrence Kasungi | Machine Operator |
|  | Ms. Lydia Nyagol | Secretary |
|  | Mr. Nasser Ahmed | Office Assistant |
|  | Ms. Fardosa Hossein | Office Assistant |
|  | Ms. Josehine Kusinyi | Principal Legal Counsel II |
|  | Ms. Sombee Toona | Legal Counsel II |
|  | Mr. Malcolm Ngugi | Legal Counsel II |
|  | Ms. Regina Munyao | Legal Clerk I |
|  | Ms. Shelmith Miano | Personal Secretary |
|  | Maj. Joel Nkubitu (Rtd) | DCSAA |
|  | Mr. Wilson Bosmet | Principal SAA |
|  | Mr. Onesmus Kilimo | SAA I |
|  | Mr. John Pere | SAA III |
|  | Mr. Patrick Murindo | SAA III |
|  | Ms. Sarah Rukwaro | Assistant SAA |
|  | Mr. James Ngusya | Assistant SAA |
|  | Ms. Lucy Mwaniki | Assistant SAA |
|  | Mr. Godana Mamo | SAA III |
|  | Ms. Julia Gachoki | Senior Commissionaire |
|  | Mr. Abdihabib Dekow | Senior Commissionaire |
|  | Ms. Hawa Abdi | Senior Commissionaire |
|  | Inspector Joseph Kiptoo | Inspector |
|  | Sgt. Daniel Koibir | Sergeant |
|  | PC Jamal Dabasso | Police Constable |
|  | Ms. Farida Ngasura | Audio Supervisor |
|  | Mr. John Mungai | Audio Officer III |
|  | Mr. Robert Rop | Audio Technician |
|  | Ms. Christine Maeri | Audio Officer III |
|  | Mr. Abdikhani Kala | Audio Officer III |
|  | Ms. Moureen Kweyu | Intern |
|  | Ms. Joyce Chelangat | Intern |
|  | Ms. Charity Ngugi | Security Supervisor I |
|  | Mr. James Muriuki | Security Supervisor I |
|  | Mr. Robert Kosgey | Security Warden |
|  | Ms. Joy Mercy | Security Warden |
|  | Mr. Jacob Makau | Security Warden |
|  | Mr. Alex Rithi | Media Relations Officer 1 |
|  | Ms. Lucianne Limo | Media Relations Officer |
|  | Ms. Njeri Manga | Media Relations Officer |
|  | Mr. Ibrahim Oruko | Daily Nation |
|  | Ms. Rosylen Obala | Standard |
|  | Mr. Julius Otieno | The Star |
|  | Mr. Hilary Mageka | People |
|  | Mr. Patrick Amimo | KTN |
|  | Ms. Jane Goin | Citizen |
|  | Mr. Kennedy Murithi | NTV |
|  | Mr. Daniel Kariuki | K24 |
|  | Mr. Edward Kabasa | KBC |
|  | Mr. Japhet Muthomi | Chief Public Communication Officer |
|  | Mr. Eric Ogolo | Public Communication Officer |
|  | Ms. Faith Nthenge | Public Communication Assistant |
|  | Mr. Eliud Matumbai | Public Communication Assistant |
|  | Ms. Brigid Sielei | Public Communication Assistant |
|  | Ms. Belinda Mugasia | Printer III |
|  | Ms. Shedho Liban | Finance Officer II |
|  | Mr. Victor Kavate | Accountant III |
|  | Diana Kimetto | Ag. Principal HRMO |
|  | Benard Chesoli | HRM Officer III |
|  | Ms. Rose Mailu | F&B Supervisor |
|  | Ms. Evelyne Mwangi | Head Waitress |
|  | Mr. Martin Madanji | Chef De’Partie |
|  | Ms. Musyoka Venza | Senior Waiter |
|  | Ms. Mercy Ondego | Waitress |
|  | Mr. Aerial Kairu | Waiter |
|  | Ms. Margaret Ngéi | Cook |
|  | Mr. Ignatius Ekalale | Cook |
|  | Mr. Samuel Kanuku | Transport Officer |
|  | Mr. Caleb Machuki | Telephone Supervisor |
|  | Mr. Joel Espira | Physiotherapist |
|  | Mr. John Adeya | Kit custodian |
|  | Ms. Roselynne Omolloh | Director, Speaker’s Office |
|  | Mr. Fredrick Muthengi | Chief Fiscal Analyst |
|  | Ms. Julie Mwithiga | Fiscal Analyst II |
|  | Ms. Lucy Radoli | Legal Counsel II |
|  | Mr. Mitchel Otoro | Legal Counsel II |
|  | Mr. Richard Njoroge | Electronics Officer |
|  | Ms. Esther Kariuki | Office Assistant |
|  | Mr. Justine Ongwén | Driver |
|  | CPL. Joel Khamadi | Security Aide |